## Info
Race Name: | Mistletoe Runs
Race Date: | 2005-12-03
| Half | 5K
Distance: | 13.1 | 3.1
Registration Start: | 6:30 | 6:30
Event Time: | 8:30 | 8:45
Desired Water Stops: | 6 | 2
Actual Water Stops | 8 | 2
Number of Turns: | 14 | 2
Winning Time: | 1:10 | 0:16
Average Pace | 0:05 | 0:05
Final Finisher: | 3:34 | 1:15
Average Pace | 0:16 | 0:24
Estimated Runners: | 700 | 500
Race Day Fee: | 30 | 30
Preregistration Fee: | 25 | 25
Preregistration %: | 90% | 90%
Volunteers
Course | 27 | 5
Registration | 12 | 9
Water Stops | 32 | 8
Water Requirements: |  |  | Total
Cups | 12600 | 3000 | 15600
Gallons at each stop: | 44 | 32 | 76
Gallons at start/finish: | 88 | 64 | 152
Porta-Jons: | 17 | 12
Race-Director: | Beth Hair
Co-Director:
Site Logistics Chair:
Sponsors & Donations Chair:
Publicity & Promotion Chair:
Registration Chair:
Aid Station Chair:
Results Chair: | Keith Stone
Finish Line (timing) Chair 1:
Finish Line (timing) Chair 2:
Time at each mile mark: | Leader | Leader | Trailer | Trailer
1 | 8:35 | 8:50 | 8:46 | 9:09
2 | 8:41 | 8:56 | 9:03 | 9:33
3 | 8:46 | 9:01 | 9:19 | 9:58
4 | 8:51 | 9:06 | 9:35 | 10:22
5 | 8:57 | 9:12 | 9:52 | 10:46
6 | 9:02 | 9:17 | 10:08 | 11:10
7 | 9:07 | 9:22 | 10:24 | 11:34
8 | 9:13 | 9:28 | 10:41 | 11:59
9 | 9:18 | 9:33 | 10:57 | 12:23
10 | 9:23 | 9:38 | 11:13 | 12:47
11 | 9:29 | 9:44 | 11:30 | 13:11
12 | 9:34 | 9:49 | 11:46 | 13:35
13 | 9:39 | 9:54 | 12:02 | 14:00
14 | 9:45 | 10:00 | 12:19 | 14:24
15 | 9:50 | 10:05 | 12:35 | 14:48
16 | 9:55 | 10:10 | 12:51 | 15:12
17 | 10:01 | 10:15 | 13:08 | 15:36
18 | 10:06 | 10:21 | 13:24 | 16:00

## Budget
Expenses
|  |  | Each | Quantity | Total
Printing
|  | Brochures | 0 | 0 | 0
|  | Posters | 0 | 0 | 0
|  | Race Bibs | 0.3 | 700 | 210
|  | Mailing Labels | 0 | 0 | 0
|  | Signage | 0 | 0 | 0
|  | Banners | 0 | 0 | 0
Administration:
|  | Race Director Fees | 1000 | 0 | 0
|  | Finish Line Fees | 450 | 0 | 0
|  | Police Support | 70 | 0 | 0
|  | On-Site Security | 0 | 0 | 0
|  | Insurance | 250 | 1 | 250
|  | Mailing | 0 | 0 | 0
|  | Course Certification | 150 | 0 | 0
|  | Rescue Squad | 125 | 1 | 125
|  | Misc Supplies | 50 | 1 | 50
Refreshments:
|  | Beer | 0 | 0 | 0
|  | Fruit | 0 | 0 | 0
|  | Electrolyte Drinks | 0 | 0 | 0
|  | Water | 0 | 0 | 0
|  | Cups | 0 | 0 | 0
Equipment
|  | PA Systems | 150 | 0 | 0
|  | Tents | 50 | 0 | 0
|  | Tables | 25 | 0 | 0
|  | Portable Toilets | 75 | 10 | 750
Runner Spifs
|  | T-shirts | 5 | 1236 | 6180
|  | X-Large |  | 540
|  | Large |  | 540
|  | Medium |  | 168
|  | Small |  | 12
|  | Finisher Medals | 0 | 700 | 0
|  | Screen Printing | 1 | 1236 | 1236
Advertising:
|  | Design & Productioon |  |  | 0
|  | Television |  |  | 0
|  | Newspaper |  |  | 0
|  | Radio |  |  | 0
|  | Regional Publications | 30 | 2 | 60
|  | National Publications |  |  | 0
|  | Photography |  |  | 0
Awards:
|  | Medals |  |  | 0
|  | Trophies |  |  | 0
|  | Prize Money |  |  | 0
|  | Total Expenses |  |  | 8861
Revenues
Entry Fees:
|  | Runners Fees | 30 | 70 | 2100
|  | Pregistration: | 25 | 630 | 15750
|  | Walkers Fees | 30 | 50 | 1500
|  |  | 25 | 450 | 11250
Sponsors:
Sponsor A
Sponsor B
Sponsor C
|  | Total Revenue |  |  | 30600
|  | Net Gain (Loss) |  |  | 21739

## Check Lists
Before Race is Advertised |  | Responsibility
| Review proposed race brochure and make sure it's complete and encouraged legibility. Full name including middle initial, address, city, state, ZIP, phone, email, birth date, age on race day and gender need to be on the form. | TCTC Board, Event Coordinator
| Communicate prices, dates, cut-offs, and contact information to webmaster to set-up online registration and web calendar. | Race & Equipment, Event Coordinator, Webmaster
Advertising the Race |  | Responsibility
| Create online registration and web calendar | Webmaster, Event Coordinator
| Deliver 600 brochures to Flyer Editor | Event Coordinator, Flyer Editor
| Submit race to Winston Salem Journal, CoolRunning.com, RunnersWorld.Com | Event Coordinator, Race & Equipment
| Select list for direct mail campaign | Webmaster, Event Coordinator
Information Needed Before Race Week |  | Responsibility
| Obtain bib number range from race organizers | Finish Line Director, Results Coordinator, Event Coordinator
| Verify age groups and awards and communicate that to results personnel | Finish Line Director, Results Coordinator, Event Coordinator
Wednesday Before Race |  | Responsibility
| Complete pre-registration data entry | Event Registration Coordinator
| Turn off online registration | Webmaster
| Send file of pre-registered runners to club database manager | Event Registration Coordinator
| Merge mail-in and online registration | Webmaster
| Assign bib numbers | Webmaster
| Print bib labels | Webmaster
| Print pre-registration lists | Webmaster
| Create RunScore file for laptop | Webmaster
Night Before Race |  | Responsibility
| Check each Time Machine bag (blue bags) and verify there is a plunger, charger, and DB-9 computer cable. | Race & Equipment, Finish Line Director
| Plug in Time Machine and clocks. You'll need at least two clocks and Time Machines. | Race & Equipment, Finish Line Director
| Check the race pack and verify there are stringers, duct tape, WD-40, Pens, Paper Punch, Bandit tags and registration signs. You'll need one stringer for each 25 runners and at least one bandit tag per stringer. | Race & Equipment, Finish Line Director
Check the laptops and make sure they come up, and that the printer works and has paper.
| Check the silver case and make sure the gun is there and has bullets. Verify that there is one working stopwatch for each mile and two additional watches for the finish line. | Race & Equipment, Finish Line Director
What to tell Registration People Before Registration Starts |  | Responsibility
Only one name per registration form.
They need to validate that entry forms are legible.
They MUST write the name, age, and sex on the bib tear-off and they must write the bib number clearly on the entry form before giving the bib to the participant.
They need to inform participants that the bib must be on the front and visible and that they should NOT tear off anything before the race finishes.
What to Tell Finish Line People Before Race Starts |  | Responsibility
| People pulling tags must place them FACE DOWN on the string and not gather them in their hand. | Finish Line Director
What to Announce at Start |  | Responsibility
| People must were their bib visibly | Event Coordinator, Finish Line Director
Equipment Checklist |  | Responsibility
Every Race
| Handheld PA (charged) | Race & Equipment, Finish Line Director
| Mile Markers (one for each mile) | Race & Equipment, Finish Line Director
| Time Machines (charged) | Race & Equipment, Finish Line Director
| Digital Clocks (charged) | Race & Equipment, Finish Line Director
| Race Pack with stringers, duct tape, WD-40, pens, registration signs, bandit tags, paper punch | Race & Equipment, Finish Line Director
| Cones | Race & Equipment, Finish Line Director
| Case with Starter Pistol and stop watches | Race & Equipment, Finish Line Director
| At least one table for timers | Race & Equipment, Finish Line Director
| At least three chairs for timers | Race & Equipment, Finish Line Director
| Finish banner and stanchions | Race & Equipment, Finish Line Director
| Chute Materials (stanchions, flagging) | Race & Equipment, Finish Line Director
| Clipboards | Race & Equipment, Finish Line Director
| Every TCTC Race | Responsibility
| Coolers | Race & Equipment, Finish Line Director
| Ice | Race & Equipment, Finish Line Director
| Water | Race & Equipment, Finish Line Director
| Gatorade | Race & Equipment, Finish Line Director
| Tables for registration and food | Race & Equipment, Finish Line Director
| Chairs for registration and food | Race & Equipment, Finish Line Director
| Sound System | Race & Equipment, Finish Line Director
| TCTC Banners | Race & Equipment, Finish Line Director
| Paper Cups | Race & Equipment, Finish Line Director
| Trash Bags | Race & Equipment, Finish Line Director
| Tents | Race & Equipment, Finish Line Director
| Safety Pins | Race & Equipment, Finish Line Director
| Bibs | Race & Equipment, Finish Line Director
| 1st Aid Kit | Race & Equipment, Finish Line Director
| Ultimate | Responsibility
| Tongue Depressors #1-114 | Race & Equipment, Finish Line Director
| Tongue Depressors #1-20 | Race & Equipment, Finish Line Director
| Orange Starter Flags & Gloves | Race & Equipment, Finish Line Director
| At least 100 caps for the starter pistol | Race & Equipment, Finish Line Director
| Tape for posting results | Race & Equipment, Finish Line Director
| Stapler (and staples) | Race & Equipment, Finish Line Director
| Water Hoses (at least 200 feet) | Race & Equipment, Finish Line Director
| Extension cords | Race & Equipment, Finish Line Director

## Time Line
Task | Notes | Date | Time | Assigned To
Sponsors and donations committee and chair established |  | 2005-06-06 |  | Keith Stone
Notify Runner's World |  | 2005-08-01 |  | Keith Stone
Notify Running Times |  | 2005-08-01 |  | Keith Stone
Select course |  | 2005-08-01
Notify Police |  | 2005-08-05
Publicity and promotion committee and chair established |  | 2005-08-05
Buy ads in Running Journal |  | 2005-09-01
Obtain Parade Permit |  | 2005-09-04
Obtain State Permits |  | 2005-09-04
Print Brochures |  | 2005-09-04 |  | Keith Stone
Print Posters |  | 2005-09-04
Obtain USATF Sanction or other insurance |  | 2005-10-01
Direct Mailing |  | 2005-10-04 |  | Keith Stone
Order Awards |  | 2005-10-04 |  | N/A
Get race brochures in TCTC newsletter |  | 2005-10-15
Obtain Certificates of Insurance |  | 2005-10-15
Order Race Bibs |  | 2005-10-19
Registration committee and chair established |  | 2005-10-19
Aid stations committee and chair established |  | 2005-11-03
Awards committee and chair established |  | 2005-11-03
Clean-up committee and chair established |  | 2005-11-03
Course volunteers committee and chair established |  | 2005-11-03
Medical committee and chair established |  | 2005-11-03
Refreshments committee and chair established |  | 2005-11-03
Results committee and chair established |  | 2005-11-03
Finish line (timing) committee and chair established |  | 2005-11-03
Complete Course Measurement & Certification |  | 2005-11-19
Order T-shirts |  | 2005-11-19
Fire department notified |  | 2005-11-26
Medical services arranged or notified |  | 2005-11-26
Police Liaison/details arranged |  | 2005-11-26
Press/Course vehicles obtained |  | 2005-11-26
Safety pins obtained |  | 2005-11-26
Signage prepared for course and race site |  | 2005-11-26
T-shirts/other give-away items obtained |  | 2005-11-26
Get cash for race date registration |  | 2005-12-01
Entry fees deposited |  | 2005-12-02
Entry forms filed in numerical order |  | 2005-12-02
Pick up cups for water |  | 2005-12-02
Pick up food |  | 2005-12-02
Place course Mile Markers |  | 2005-12-03 | 7:30
Runner's information prepared for distribution and/or posting on race day: |  | 2005-12-03 | 5:30
Distribute or post medical/weather information |  | 2005-12-03 | 5:30
Distribute or post timing/starting line-up information |  | 2005-12-03 | 5:30
Distribute or post course map with mile markers and aid stations |  | 2005-12-03 | 5:30
Post signs for clothing drop, check-in, changing facilities, and showers |  | 2005-12-03 | 5:30
Post results |  | 2005-12-03
Volunteer/Official area assembled | Tables, chairs, signage posted, coffee, refreshments, T-shirt, Official identification, Instructional briefings prepared | 2005-12-03 | 4:30
Press area assembled | Tables, chairs, signage, copying machine, fax, race information, print-outs | 2005-12-03 | 4:30
Pre-registered runners area | List, printout posted, number pick-up, t-shirt/packet pick-up | 2005-12-03 | 4:30
Set-up race day registration area | Entry forms, pens, pencils, race numbers, safety pins, race packets, cash box, change. | 2005-12-03 | 4:30
Trouble table set-up |  | 2005-12-03 | 4:30
Course officials/marshals briefed |  | 2005-12-03 | 4:30
Start/Finish officials briefed |  | 2005-12-03 | 4:30
Official photographer(s) briefed | Provide with shot-list | 2005-12-03 | 4:30
Press/Course vehicle drivers briefed | Someone very familiar with course should serve as guide in each vehicle! | 2005-12-03 | 4:30
Trail sweep vehicle driver briefed | Provide vehicle with water, cups, blankets, first–aid kit, etc. | 2005-12-03 | 4:30
Official starter equipped and briefed |  | 2005-12-03 | 4:30
Start/finish banner(s) mounted |  | 2005-12-03 | 4:30
Start/finish review stands assembled |  | 2005-12-03 | 4:30
PA system(s) bullhorns functioning |  | 2005-12-03 | 4:30
Start/Finish line equipment in place: |  | 2005-12-03 | 4:30
pace/seeding signs |  | 2005-12-03 | 4:30
finish tape |  | 2005-12-03 | 4:30
chute materials (stanchions, rope) |  | 2005-12-03 | 4:30
digital clock |  | 2005-12-03 | 4:30
Chronomix timers |  | 2005-12-03 | 4:30
computer system (working) |  | 2005-12-03 | 4:30
recording sheets, clipboards, pencils for timers, select timers, bib number recorders |  | 2005-12-03 | 4:30
bar code spindles (if applicable) |  | 2005-12-03 | 4:30
tables/chairs |  | 2005-12-03 | 4:30
electric power hook-up (generator) |  | 2005-12-03 | 4:30
water station set-up |  | 2005-12-03 | 4:30
Restroom facilities in place |  | 2005-12-03 | 4:30
Clothing check-in in place |  | 2005-12-03 | 4:30
Medical area set-up |  | 2005-12-03 | 4:30
isolated, covered area near finish line |  | 2005-12-03 | 4:30
supervising MD and qualified nurses, EMT’s |  | 2005-12-03 | 4:30
communications |  | 2005-12-03 | 4:30
ice, IV’s, hot and cold fluids, cots, blankets |  | 2005-12-03 | 4:30
immediate triage capability |  | 2005-12-03 | 4:30
Water stations materials in place: |  | 2005-12-03 | 4:30
water/electrolyte replacement fluid |  | 2005-12-03 | 4:30
cups |  | 2005-12-03 | 4:30
pitchers |  | 2005-12-03 | 4:30
barrels/trash bags |  | 2005-12-03 | 4:30
rakes (for clean-up) |  | 2005-12-03 | 4:30
Course material in place |  | 2005-12-03 | 4:30
mile/kilometer markers |  | 2005-12-03 | 4:30
directional arrows |  | 2005-12-03 | 4:30
water/aid station markers |  | 2005-12-03 | 4:30
communication equipment/personnel (ham radio volunteers) |  | 2005-12-03 | 4:30
stop watches for mile split callers |  | 2005-12-03 | 4:30
Results area functioning: | Isolated area close to finish line, tables, chairs, electric power hook-up, computer and printer, telephone, fax, copying machine, pre-printed awards/results sheets. | 2005-12-03 | 4:30
Refreshments area functioning: | Tables, trays, ice, knives, forks, spoons (depends on foods available), napkins, trash barrels, bags | 2005-12-03 | 4:30
Awards area functioning: | Tables, chairs, podium, announcing stand, PA system, results posting board, area, awards display area, with awards arranged in order of distribution. | 2005-12-03 | 4:30
Post Race
Clean-up accomplished | Course, start and finish area, locker rooms, etc. Verify coursemarking signage is collected. | 2005-12-03
Press release with results |  | 2005-12-03
Post race stories/photos to press |  | 2005-12-03
Post race mailing to participants |  | 2005-12-10
Thank you’s to sponsors, volunteers, contributors, municipalities, facility owners |  | 2005-12-06
Post-race evaluation meeting with organizing committee |  | 2005-12-17
Volunteer/Officials party |  | 2005-12-17

## Awards
Award Worksheet
| 1st | 2nd | 3rd | 4th | 5th
Overall
Masters
Grand Masters
Clydesdale
1 To 14
14 To 17
20 To 24
25 To 29
30 To 34
35 To 39
40 To 44
45 To 49
50 To 54
55 To 59
60 To 64
65 To 69
70 To 74

## T-Shirts
X | 1462 | 42.65%
L | 1475 | 43.03%
M | 449 | 13.1%
S | 42 | 1.225%
3428